## PICO Template
| Description | Possible values | Your Production System
Project Characteristics
Project characteristics
Construction Method | Scope | {Reinforced concrete; Steel}
Building Type |  | {Residential; Commercial; Infrastructure}
Physical Description |  | {180 Apartments, 8 Floors; 11,000 Square meters}
Building Repetitiveness |  | {Unique; A similar structure was build}
Cost Scope |  | {10M; 150M}
Planned Duration |  | {9 Month; 2 Years}
Production Control Mechanisms
Coordination
Meeting types | What are the types of meetings in a work setting? | {Update/ status; Planning weekly/daily work}
Frequency of meetings | At what frequency are meetings held? | {Every day; Weekly; Monthly}
The lowest rank in the meeting | Who is the lowest rank in the meeting? | {Worker; Forman; Site engineer; Project manager; Supervisor; Business unit manager}
The most senior level in the meeting | Who is the most senior level in the meeting? | {Worker; Forman; Site engineer; Project manager; Supervisor; Business unit manager}
Employee's Situational Awareness
Delivery of Task Lists to work crews | How are the day-to-day tasks conveyed to the work crews? | {Not accessible; Available hourly/daily/weekly}
Informing work crews of new targets/goals | How are workers informed of new goals? | {Not informed; Informed daily/weekly/monthly}
Feedback on work crews' progress | How is progress feedback provided to work crews? | {Not reflected; Reflected only when in delay; Reflected hourly/daily/weekly}
Management (Company head office) Situational Awareness
Meeting performance goals | What is the frequency of reporting whether performance goals were met to management? | {Daily; Weekly; Monthly}
Attention to targets that are not expected to be met | What is the frequency of reporting on targets that are not expected to be met to management? | {Daily; Weekly; Monthly}
Proposing solutions for expected "derailment" | What is the frequency of proposing solutions for "derailment" that are not expected to be met to management? | {Daily; Weekly; Monthly}
Work Packaging
Location decomposition | What is the location decomposition? (NB distinct from the product decomposition) | {Room; Floor; Square meter}
Product decomposition | What are the basic products, how are they composed in a hierarchy? | {Assembly; Element; Component; Part}
Work Breakdown Structure | What is the work breakdown structure? How are crews composed - (by trade or by product)? | {Major trades; Trade specialization; Crew specialization; Actions}
Task Workload Balancing (Takt) | What is the task workload balance? | {None, Takt packaging; line of balance}
Scheduling Buffer Policy | What is the scheduling buffer policy? | {None for design; X hour buffer between task; 3 weeks in advance for design changes}
Production planning and control methods
Master Planning | How is the master schedule set? | {CPM; Gantt chart}
Phase Planning | How is the phase planning is detailed? | {CPM; Gantt chart; Reverse phase scheduling; DTC tools}
Look Ahead Planning/ Constraint Filtering | How is the look-ahead planning/ constraint filtering is set? | {None; CPM; Last planner system- workable backlog; DTC tools}
Short Term Work Planning | How is short term work planning performed? | {None; CPM; Last planner system- WWP, PPC; DTC tools}
Short term constraint filtering | How are tasks filtered for constraint satisfaction? What are the minimum conditions for releasing work for execution? | {None; CPM; Simulation; Pull; Push}
Process/ Optimization Policy | What is the process/ optimization policy? | {None; Minimize work waiting for workers; Minimize workers waiting for work}
Materials Management
Materials packaging policy | How are materials pre-packaged? (p.s. not the distinction between the location and products) | {No material packaging policy; By location (building/ floor/ apartment); By construction product (wall/ room); By material type}
Materials flow policy | What is the material flow policy? | {No policy; Push; Pull with preset buffer sizes; Just In Time (JIT)}
Logistic system configuration | Who manages (operates) the logistics of materials on site? | {Subcontractors; GC site managers; Independent logistic team}
Materials delivery planning | Who plans material deliveries? | {Subcontractor; Logistics team; Site Team; GC head office procurement}
Materials delivery coordination | Who coordinates material delivery with drivers? | {Subcontractor; Site Team; A dedicated department}
Equipment Management
Infrastructure equipment | Who owns the infrastructure equipment? | {Rented ; Owned by the company}
Production equipment | Who owns the equipment? | {Rented ; Owned by the company}
Hand tools policy | Who provides hand tools for trades? This is a policy decision that determines whether hand tools will be a cause of wasted time | {GC; Subcontractor; Both}
Product changes
Coordinating | How are product changes coordinated through the production line? | {Daily meetings; BIM 360; WhatsApp; E-mails}
Documenting | How are product changes documented through the production line? | {Paper; BIM 360; WhatsApp; E-mails; Sitedrive}
Process changes
Coordinating | How are process changes coordinated through the production line? | {Daily meetings; BIM 360; WhatsApp; E-mails}
Documenting | How are process changes documented through the production line? | {Paper; BIM 360; WhatsApp; E-mails; Sitedrive}
Information and Communication Technologies
Operations flow information
Trades (Workers) production rate | What are the specific trade production rates? | {No information; Experience-based trade type production rate; Historical specific trade production rate; Trade production rate variation}
Trade quality performance | What is the specific trade quality (rework/RFI) performance? | {No information; Experience-based trade type quality performance; Historical specific trade quality performance}
Work control frequency | What is the frequency of collecting information on the amount of work completed? | {Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone}
Work control resolution | What is the level of resolution of the information collected on the amount of work completed? | {No control; The number of teams on the site a day/week; The number of workers in each team on site a day/week; Work amount preformed; Type of work preformed; Adding value work duration; Not adding value work duration}
Trades constraints | Are prerequisite tasks mapped and how? | {Milestones; Gantt chart; Network diagram; Work Breakdown Structure; Computer network}
Material consumption monitoring frequency | What is the frequency at which material consumption should be monitored or detected? | {No detection; Hourly; Daily; Weekly; Monthly}
Location occupation monitoring frequency | What is the frequency of collecting information on the location occupation and remaining? | {No monitoring; Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone}
Location occupation monitoring resolution | What is the level of resolution of the information collected on the location occupation? | {No information collected; Occupied/Free of work; Occupied/Free of materials; Location expected to be cleared}
Control technologies | What type of technology is used for collecting the information? | {Site gate; Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings}
Process flow information (Product)
Product fabrication information LOD requirements | What LOD is required for information about the fabrication of the product(s), including materials? | {No materials list; Partial materials list; Detailed materials list; Detailed computerized list of materials} {Individual components; Sub-assemblies; Parameters; Type; Products; Generic categories} {Minimum (LOD100-200); Medium (LOD 300); Maximum LOD (400-500)}
Product detailing process | What process is applied for developing the required level of detail for product fabrication information? | {None; Subcontractors provide shop drawings for review; Full VDC Process; partial VDC process for selected products}
Product equipment information requirements | What information is required about the equipment needed to build the product? | {No equipment list; Partial equipment list; Detailed equipment list; Detailed computerized list of materials}
Performance monitoring technologies | What type of technology is used for collecting product information? | {Site gate; Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings}
Control technologies | What type of technology is used for collecting the information? | {Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings; Temperature and humidity measurement}
Logistics flow information
Materials location monitoring frequency | What is the frequency of collecting information on the materials location and remaining? | {No monitoring; Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone}
Materials inventory monitoring frequency | What is the frequency and extent of monitoring the material inventory? | {No monitoring; Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone}
Control Technologies | What type of technology is used for collecting material status information? | {Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings}
Equipment location and status | What type of monitoring is implemented to maintain the equipment? | {There is no inspection; Manual reports; Regular inspections and preventive maintenance schedules; A computerized maintenance management system; Maintenance logs are kept to document the maintenance activities performed on the equipment; Real-time monitoring systems}
Control Technologies | What type of technology is used for collecting equipment status information? | {Self reporting; RFID/BLE; Voice recordings}
Design status monitoring | What is the status of completing the design information? | {There is no tracking of the completion of the design; Completed before the project starts; Regular design reviews}
Platforms / Software
Production status dashboard system | What technological tools to are implemented to support information and communication? | {None; Data Visualization Tool e.g. Power BI; Project management e.g. Sitedrive}
Materials takeoff |  | {Manual; Word; Excel; BIM platforms; PDF-based collaboration and markup tools; Cloud-based construction takeoff; Estimating software}
Equipment status |  | {None; Manual; Digital Self reporting; RFID/BLE; 'Black Box' for heavy equipment}
Schedule planning |  | {Manual; Word; Excel; Cloud-based construction takeoff}
Schedule control |  | {Word; Excel; collaborative whiteboarding e.g. Miro; Project management e.g. Sitedrive, Tocoman; Site whiteboard; Site monitor}
Design coordination |  | {Manual; PDF-based collaboration and markup tools; BIM e.g. Revit, Solibri, Tekla, Simplebim; Cloud-based construction management e.g. BIM 360; Dedicated software}
Quality control |  | {Visually; Dedicated software e.g. Concrete Quality Control}
Budget control |  | {Word; Excel; collaborative whiteboarding e.g. Miro; Project management e.g. Sitedrive, Tocoman, Vico, Microsoft Business Central}
Procurement |  | {Manual; Emails; Instant messaging e.g. WhatsApp; PDF-based collaboration and markup tools; BIM e.g. Revit, Tekla, Simplebim; Cloud-based construction management e.g. BIM 360; Dedicated software e.g. Solibri, Zeroni}
Safety |  | {Dedicated software e.g. Zeroni; Email; Instant messaging e.g. WhatsApp}
Logistics |  | {Dedicated software e.g. Zeroni; Email; Instant messaging e.g. WhatsApp}
Commercial Terms
Contract
Type | What is the contract type? | {DBB; DB; CM; CM@Risk; IPD; Other}
Introduction of construction expertise | At what stage of the project design and planning process does the GC become involved? | {Program; Initial/ Final/ Detailed design; Production planning}
GC payment method | What payment methods are used for the GC? | {Quantities; Percentage from the project cost}
Designers Payment | What payment methods are used for the designers? | {Hourly; Percentage from the project cost}
Designers LOD specification | What is the required project LOD? | {Minimum (LOD100-200); Medium (LOD 300); Maximum LOD (400-500)}
Control and Flexibility of The GC
Risk | What is the level of risk associated with the project? | {No risk; X% from the project cost; Critical project, maximum risk, the project will determine if the company finishes the year in profit or loss}
Flexibility for Design Changes during production | What is the degree of design flexibility afforded by the project? | {None; Property values; Dimensional changes; Topological changes}
Design Control | To what extent does the GC have control over the design of the project? | {No control; Limited control over architecture/ structural/ plumbing/ HVAC/ electricity; Design; Full Control}
Operating Control | To what extent does the GC have control over the operating of the project? | {No control; Limited control; Full control}
Cash Flow | What are the project cash flow limitations? | {No limitations; Materials purchases limitation; Labor limitation}
Trade employment
Employment conditions | What are the employment conditions? | {Direct employment; Employment through a human resources contractor; Employment of subcontractors}
Remuneration (wage) conditions | What are the wage conditions? | {Hourly; Daily; Monthly (global payment); By product}
Induction of new workers (on-boarding) | How are new employees inducted on the site? | {There is no conversation with the new employees on behalf of the company; There is an introductory conversation only for new employees; Presenting the work status and work methodology; ___ hours/days Professional qualification required by the company}
Organizational Structure
Hierarchy
Departments/Groups/Crews | What are the different departments, groups, or crews involved in the project? | {Client representation; Design; IT; Safety; Quality; Accounting; Procurement}
Subordination (departments) | What is the subordination structure of the departments involved in the project? | {Matrix; Direct control}
Functional roles | What are the functional roles involved in the project? | {Manager; Designer; Finance; Quality}
Subordination (roles) | What is the subordination of the departments involved in the project? | {}
Functional role parameters
Scope/responsibility | What is the scope or responsibility of the functional roles involved in the project? | {Ordering materials; IT support; Generate reports}
Deliverables | What are the required deliverables for each functional role involved in the production phase? | {Generate reports; Design agreements}

## PICO Case Study
| Description | Possible values | Case Study - Weekly Takt Example
Project Characteristics
Project characteristics
Construction Method | Scope | {Reinforced concrete; Steel} | Precast concrete
Building Type |  | {Residential; Commercial; Infrastructure} | Residential
Physical Description |  | {180 Apartments, 8 Floors; 11,000 Square meters} | 7 Floors, 5-6 apartments per Floor
Building Repetitiveness |  | {Unique; A similar structure was build} | A similar structure was build
Cost Scope |  | {10M; 150M} | 7 M
Planned Duration |  | {9 Month; 2 Years} | 16 Month
Production Control Mechanisms
Coordination
Meeting types | What are the types of meetings in a work setting? | {Update/ status; Planning weekly/daily work} | Planning weekly/daily work
Frequency of meetings | At what frequency are meetings held? | {Every day; Weekly; Monthly} | Weekly
The lowest rank in the meeting | Who is the lowest rank in the meeting? | {Worker; Forman; Site engineer; Project manager; Supervisor; Business unit manager} | Worker
The most senior level in the meeting | Who is the most senior level in the meeting? | {Worker; Forman; Site engineer; Project manager; Supervisor; Business unit manager} | Project manager
Employee's Situational Awareness
Delivery of Task Lists to work crews | How are the day-to-day tasks conveyed to the work crews? | {Not accessible; Available hourly/daily/weekly} | Available weekly
Informing work crews of new targets/goals | How are workers informed of new goals? | {Not informed; Informed daily/weekly/monthly} | Informed weekly
Feedback on work crews' progress | How is progress feedback provided to work crews? | {Not reflected; Reflected only when in delay; Reflected hourly/daily/weekly} | Reflected weekly
Management (Company head office) Situational Awareness
Meeting performance goals | What is the frequency of reporting whether performance goals were met to management? | {Daily; Weekly; Monthly} | Daily
Attention to targets that are not expected to be met | What is the frequency of reporting on targets that are not expected to be met to management? | {Daily; Weekly; Monthly} | Weekly
Proposing solutions for expected "derailment" | What is the frequency of proposing solutions for "derailment" that are not expected to be met to management? | {Daily; Weekly; Monthly} | Weekly
Work Packaging
Location decomposition | What is the location decomposition? (NB distinct from the product decomposition) | {Room; Floor; Square meter} | Floor
Product decomposition | What are the basic products, how are they composed in a hierarchy? | {Assembly; Element; Component; Part} | Floor
Work Breakdown Structure | What is the work breakdown structure? How are crews composed - (by trade or by product)? | {Major trades; Trade specialization; Crew specialization; Actions} | Trade specialization
Task Workload Balancing (Takt) | What is the task workload balance? | {None, Takt packaging; line of balance} | Takt packaging and line of balance
Scheduling Buffer Policy | What is the scheduling buffer policy? | {None for design; X hour buffer between task; 3 weeks in advance for design changes} | Between one and four working days
Production planning and control methods
Master Planning | How is the master schedule set? | {CPM; Gantt chart} | CPM and Gantt chart
Phase Planning | How is the phase planning is detailed? | {CPM; Gantt chart; Reverse phase scheduling; DTC tools} | CPM and Gantt chart
Look Ahead Planning/ Constraint Filtering | How is the look-ahead planning/ constraint filtering is set? | {None; CPM; Last planner system- workable backlog; DTC tools} | CPM and Last planner system- workable backlog
Short Term Work Planning | How is short term work planning performed? | {None; CPM; Last planner system- WWP, PPC; DTC tools} | CPM, Last planner system- WWP, PPC, and partially DTC tools
Short term constraint filtering | How are tasks filtered for constraint satisfaction? What are the minimum conditions for releasing work for execution? | {None; CPM; Simulation; Pull; Push}
Process/ Optimization Policy | What is the process/ optimization policy? | {None; Minimize work waiting for workers; Minimize workers waiting for work} | {Minimize work waiting for workers; Minimize workers waiting for work}
Materials Management
Materials packaging policy | How are materials pre-packaged? (p.s. not the distinction between the location and products) | {No material packaging policy; By location (building/ floor/ apartment); By construction product (wall/ room); By material type} | By apartment
Materials flow policy | What is the material flow policy? | {No policy; Push; Pull with preset buffer sizes; Just In Time (JIT)} | 2 Weeks external storage buffer
Logistic system configuration | Who manages (operates) the logistics of materials on site? | {Subcontractors; GC site managers; Independent logistic team} | 70% of the materials are managed by the general contractor. The rest is managed by the subcontractors.
Materials delivery planning | Who plans material deliveries? | {Subcontractor; Logistics team; Site Team; GC head office procurement} | The site team (foremen, site manager, site engineer)
Materials delivery coordination | Who coordinates material delivery with drivers? | {Subcontractor; Site Team; A dedicated department} | Subcontractor and Site Team
Equipment Management
Infrastructure equipment | Who owns the infrastructure equipment? | {Rented ; Owned by the company} | Rented
Production equipment | Who owns the equipment? | {Rented ; Owned by the company} | Some rented and some owned by the company
Hand tools policy | Who provides hand tools for trades? This is a policy decision that determines whether hand tools will be a cause of wasted time | {GC; Subcontractor; Both} | GC and Subcontractors
Product changes
Coordinating | How are product changes coordinated through the production line? | {Daily meetings; BIM 360; WhatsApp; E-mails} | Daily meetings, WhatsApp, and E-mails
Documenting | How are product changes documented through the production line? | {Paper; BIM 360; WhatsApp; E-mails; Sitedrive} | NON, Sitedrive, and WhatsApp
Process changes
Coordinating | How are process changes coordinated through the production line? | {Daily meetings; BIM 360; WhatsApp; E-mails} | Daily meetings, WhatsApp, and E-mails
Documenting | How are process changes documented through the production line? | {Paper; BIM 360; WhatsApp; E-mails; Sitedrive} | None, Sitedrive, and WhatsApp
Information and Communication Technologies
Operations flow information
Trades (Workers) production rate | What are the specific trade production rates? | {No information; Experience-based trade type production rate; Historical specific trade production rate; Trade production rate variation} | Experienced based trade type production rate
Trade quality performance | What is the specific trade quality (rework/RFI) performance? | {No information; Experience-based trade type quality performance; Historical specific trade quality performance} | Experienced based trade type quality performance
Work control frequency | What is the frequency of collecting information on the amount of work completed? | {Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone} | Weekly
Work control resolution | What is the level of resolution of the information collected on the amount of work completed? | {No control; The number of teams on the site a day/week; The number of workers in each team on site a day/week; Work amount preformed; Type of work preformed; Adding value work duration; Not adding value work duration} | The number of workers in each team on site a day, Work amount preformed, Type of work preformed
Trades constraints | Are prerequisite tasks mapped and how? | {Milestones; Gantt chart; Network diagram; Work Breakdown Structure; Computer network} | Gantt chart
Material consumption monitoring frequency | What is the frequency at which material consumption should be monitored or detected? | {No detection; Hourly; Daily; Weekly; Monthly} | Weekly
Location occupation monitoring frequency | What is the frequency of collecting information on the location occupation and remaining? | {No monitoring; Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone} | Weekly
Location occupation monitoring resolution | What is the level of resolution of the information collected on the location occupation? | {No information collected; Occupied/Free of work; Occupied/Free of materials; Location expected to be cleared} | Occupied/Free of work and Location expected to be cleared
Control technologies | What type of technology is used for collecting the information? | {Site gate; Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings} | Site gate and Self reporting
Process flow information (Product)
Product fabrication information LOD requirements | What LOD is required for information about the fabrication of the product(s), including materials? | {No materials list; Partial materials list; Detailed materials list; Detailed computerized list of materials} {Individual components; Sub-assemblies; Parameters; Type; Products; Generic categories} {Minimum (LOD100-200); Medium (LOD 300); Maximum LOD (400-500)} | Medium (LOD 300)
Product detailing process | What process is applied for developing the required level of detail for product fabrication information? | {None; Subcontractors provide shop drawings for review; Full VDC Process; partial VDC process for selected products} | Subcontractors provide shop drawings for review
Product equipment information requirements | What information is required about the equipment needed to build the product? | {No equipment list; Partial equipment list; Detailed equipment list; Detailed computerized list of materials} | Partial equipment list
Performance monitoring technologies | What type of technology is used for collecting product information? | {Site gate; Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings} | Self reporting
Control technologies | What type of technology is used for collecting the information? | {Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings; Temperature and humidity measurement} | Self reporting, Temperature and humidity measurement;
Logistics flow information
Materials location monitoring frequency | What is the frequency of collecting information on the materials location and remaining? | {No monitoring; Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone} | Weekly
Materials inventory monitoring frequency | What is the frequency and extent of monitoring the material inventory? | {No monitoring; Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone} | Weekly
Control Technologies | What type of technology is used for collecting material status information? | {Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings} | Digital self reporting
Equipment location and status | What type of monitoring is implemented to maintain the equipment? | {There is no inspection; Manual reports; Regular inspections and preventive maintenance schedules; A computerized maintenance management system; Maintenance logs are kept to document the maintenance activities performed on the equipment; Real-time monitoring systems} | Regular inspections and preventive maintenance schedules
Control Technologies | What type of technology is used for collecting equipment status information? | {Self reporting; RFID/BLE; Voice recordings} | Self reporting
Design status monitoring | What is the status of completing the design information? | {There is no tracking of the completion of the design; Completed before the project starts; Regular design reviews} | Regular design reviews
Platforms / Software
Production status dashboard system | What technological tools to are implemented to support information and communication? | {None; Data Visualization Tool e.g. Power BI; Project management e.g. Sitedrive} | Sitedrive
Materials takeoff |  | {Manual; Word; Excel; BIM platforms; PDF-based collaboration and markup tools; Cloud-based construction takeoff; Estimating software} | Excel; BIM platforms
Equipment status |  | {None; Manual; Digital Self reporting; RFID/BLE; 'Black Box' for heavy equipment} | Manual
Schedule planning |  | {Manual; Word; Excel; Cloud-based construction takeoff} | Word, Excel, Miro, tocoman, Sitedrive, and Site whiteboard
Schedule control |  | {Word; Excel; collaborative whiteboarding e.g. Miro; Project management e.g. Sitedrive, Tocoman; Site whiteboard; Site monitor} | Sitedrive; Site whiteboard
Design coordination |  | {Manual; PDF-based collaboration and markup tools; BIM e.g. Revit, Solibri, Tekla, Simplebim; Cloud-based construction management e.g. BIM 360; Dedicated software} | Simplebim, and Solibri
Quality control |  | {Visually; Dedicated software e.g. Concrete Quality Control} | Concrete Quality Control and on site solutions
Budget control |  | {Word; Excel; collaborative whiteboarding e.g. Miro; Project management e.g. Sitedrive, Tocoman, Vico, Microsoft Business Central} | Excel and Tocoman
Procurement |  | {Manual; Emails; Instant messaging e.g. WhatsApp; PDF-based collaboration and markup tools; BIM e.g. Revit, Tekla, Simplebim; Cloud-based construction management e.g. BIM 360; Dedicated software e.g. Solibri, Zeroni} | Zeroni, Email, and WhatsApp
Safety |  | {Dedicated software e.g. Zeroni; Email; Instant messaging e.g. WhatsApp} | Zeroni, Email, and WhatsApp
Logistics |  | {Dedicated software e.g. Zeroni; Email; Instant messaging e.g. WhatsApp} | Zeroni, Email, and WhatsApp
Commercial Terms
Contract
Type | What is the contract type? | {DBB; DB; CM; CM@Risk; IPD; Other} | {DBB; DB; CM}
Introduction of construction expertise | At what stage of the project design and planning process does the GC become involved? | {Program; Initial/ Final/ Detailed design; Production planning} | {Program; Initial/ Final/ Detailed design; Production planning}
GC payment method | What payment methods are used for the GC? | {Quantities; Percentage from the project cost} | Percentage of the project cost
Designers Payment | What payment methods are used for the designers? | {Hourly; Percentage from the project cost} | Percentage of the project cost
Designers LOD specification | What is the required project LOD? | {Minimum (LOD100-200); Medium (LOD 300); Maximum LOD (400-500)} | Medium
Control and Flexibility of The GC
Risk | What is the level of risk associated with the project? | {No risk; X% from the project cost; Critical project, maximum risk, the project will determine if the company finishes the year in profit or loss} | No risk
Flexibility for Design Changes during production | What is the degree of design flexibility afforded by the project? | {None; Property values; Dimensional changes; Topological changes} | Minor changes
Design Control | To what extent does the GC have control over the design of the project? | {No control; Limited control over architecture/ structural/ plumbing/ HVAC/ electricity; Design; Full Control} | Limited control over architecture/ structural/ plumbing/ HVAC/ electricity. None of the designers is obligated to accept any change the GC will offer.
Operating Control | To what extent does the GC have control over the operating of the project? | {No control; Limited control; Full control} | Limited control. Higher subcontractor payments mean higher commitment, but this commitment is often stretched.
Cash Flow | What are the project cash flow limitations? | {No limitations; Materials purchases limitation; Labor limitation} | Average cash flow for Materials purchases limitation; Labor limitation
Trade employment
Employment conditions | What are the employment conditions? | {Direct employment; Employment through a human resources contractor; Employment of subcontractors} | Employment through a human resources contractor and employment of subcontractors
Remuneration (wage) conditions | What are the wage conditions? | {Hourly; Daily; Monthly (global payment); By product} | By product (square m/ unit etc.) Mistakes will be compensated hourly
Induction of new workers (on-boarding) | How are new employees inducted on the site? | {There is no conversation with the new employees on behalf of the company; There is an introductory conversation only for new employees; Presenting the work status and work methodology; ___ hours/days Professional qualification required by the company} | Presenting the work status and work methodology for new employees
Organizational Structure
Hierarchy
Departments/Groups/Crews | What are the different departments, groups, or crews involved in the project? | {Client representation; Design; IT; Safety; Quality; Accounting; Procurement} | Developer, Clients (apartment purchases), Design, IT, Accounting, HR, Procurement (contains safety and quality), logistics and suppliers.
Subordination (departments) | What is the subordination structure of the departments involved in the project? | {Matrix; Direct control} | Matrix and direct control
Functional roles | What are the functional roles involved in the project? | {Manager; Designer; Finance; Quality} | Developer, Clients (apartment purchases), Designers, IT support and developing, Accounting, HR, Procurement (contains safety and quality), business unit managers, site engineers, site managers, foremen, subcontractors, workers, logistics crew, suppliers.
Subordination (roles) | What is the subordination of the departments involved in the project? | {} | See attached organizational subordination figure 1
Functional role parameters
Scope/responsibility | What is the scope or responsibility of the functional roles involved in the project? | {Ordering materials; IT support; Generate reports} | IT: support, generate reports, developing assisting tech tools; Accounting: generate reports, company budget control, collection; HR: recruits, organizational consultant; Procurement: Contracting with suppliers, suppliers performance, materials compliance, monitoring the quality of suppliers, managing monitoring and quality and safety control, procurement of materials and equipment, contracting with subcontractors, inventory planning and vendor selection; Site team: schedule design and control, managing the site, maintaining safety regulations, supervising and maintaining quality, managing the project budget, ordering materials, ordering equipment, coordinating schedules, monitoring, and control work performance.
Deliverables | What are the required deliverables for each functional role involved in the production phase? | {Generate reports; Design agreements} | Buildings, reports, recommendations, initiating optimization and improvement processes, contracts.
Figure 1: FIRA's Organizational subordination

## Examples
| Description | Possible values | Examples for Standard Production System Types
|  |  | Traditional | Location Based
Project Characteristics
Project characteristics
Construction Method | Scope | {Reinforced concrete; Steel} | Cast in place | Cast in place
Building Type |  | {Residential; Commercial; Infrastructure} | Residential | Residential
Physical Description |  | {180 Apartments, 8 Floors; 11,000 Square meters}
Building Repetitiveness |  | {Unique; A similar structure was build} | Repetitive building | Repetitive building
Cost Scope |  | {10M; 150M}
Planned Duration |  | {9 Month; 2 Years}
Production Control Mechanisms
Coordination
Meeting types | What are the types of meetings in a work setting? | {Update/ status; Planning weekly/daily work} | Planning weekly | Update/ status
Frequency of meetings | At what frequency are meetings held? | {Every day; Weekly; Monthly} | Weekly; Monthly | Weekly; Monthly
The lowest rank in the meeting | Who is the lowest rank in the meeting? | {Worker; Forman; Site engineer; Project manager; Supervisor; Business unit manager} | Forman; Site engineer; Project manager; Supervisor; Business unit manager | Forman; Site engineer; Project manager; Supervisor; Business unit manager
The most senior level in the meeting | Who is the most senior level in the meeting? | {Worker; Forman; Site engineer; Project manager; Supervisor; Business unit manager} | Forman; Site engineer; Project manager; Supervisor; Business unit manager | Forman; Site engineer; Project manager; Supervisor; Business unit manager
Employee's Situational Awareness
Delivery of Task Lists to work crews | How are the day-to-day tasks conveyed to the work crews? | {Not accessible; Available hourly/daily/weekly} | None | Available weekly
Informing work crews of new targets/goals | How are workers informed of new goals? | {Not informed; Informed daily/weekly/monthly} | None | Informed weekly
Feedback on work crews' progress | How is progress feedback provided to work crews? | {Not reflected; Reflected only when in delay; Reflected hourly/daily/weekly} | When there is a delay | Reflected weekly
Management (Company head office) Situational Awareness
Meeting performance goals | What is the frequency of reporting whether performance goals were met to management? | {Daily; Weekly; Monthly} | Monthly | Weekly
Attention to targets that are not expected to be met | What is the frequency of reporting on targets that are not expected to be met to management? | {Daily; Weekly; Monthly} | Monthly and weekly | Monthly and weekly
Proposing solutions for expected "derailment" | What is the frequency of proposing solutions for "derailment" that are not expected to be met to management? | {Daily; Weekly; Monthly} | Monthly | Monthly and weekly
Work Packaging
Location decomposition | What is the location decomposition? (NB distinct from the product decomposition) | {Room; Floor; Square meter} | Floor, building | Floor, building
Product decomposition | What are the basic products, how are they composed in a hierarchy? | {Assembly; Element; Component; Part} | Floor, building | Floor, building
Work Breakdown Structure | What is the work breakdown structure? How are crews composed - (by trade or by product)? | {Major trades; Trade specialization; Crew specialization; Actions} | Trade specialization | Trade specialization
Task Workload Balancing (Takt) | What is the task workload balance? | {None, Takt packaging; line of balance} |  | Line of balance
Scheduling Buffer Policy | What is the scheduling buffer policy? | {None for design; X hour buffer between task; 3 weeks in advance for design changes} | Several months at the end of the project | Several months at the end of the project
Production planning and control methods
Master Planning | How is the master schedule set? | {CPM; Gantt chart} | {CPM; Gantt chart} | CPM
Phase Planning | How is the phase planning is detailed? | {CPM; Gantt chart; Reverse phase scheduling; DTC tools} | {CPM; Gantt chart; Reverse phase scheduling} | {CPM; Reverse phase scheduling}
Look Ahead Planning/ Constraint Filtering | How is the look-ahead planning/ constraint filtering is set? | {None; CPM; Last planner system- workable backlog; DTC tools} | {None; CPM; Last planner system- workable backlog} | {CPM; Last planner system- workable backlog}
Short Term Work Planning | How is short term work planning performed? | {None; CPM; Last planner system- WWP, PPC; DTC tools} | {None; CPM; Last planner system- WWP, PPC; DTC tools} | {CPM; Last planner system- WWP, PPC; DTC tools}
Short term constraint filtering | How are tasks filtered for constraint satisfaction? What are the minimum conditions for releasing work for execution? | {None; CPM; Simulation; Pull; Push}
Process/ Optimization Policy | What is the process/ optimization policy? | {None; Minimize work waiting for workers; Minimize workers waiting for work} | {None; Minimize work waiting for workers; Minimize workers waiting for work} | {Minimize work waiting for workers and Minimize workers waiting for work}
Materials Management
Materials packaging policy | How are materials pre-packaged? (p.s. not the distinction between the location and products) | {No material packaging policy; By location (building/ floor/ apartment); By construction product (wall/ room); By material type} | {No material packaging policy; By building/ floor/ apartment; By material type} | {By building/ floor/ apartment; By material type; By work packaging}
Materials flow policy | What is the material flow policy? | {No policy; Push; Pull with preset buffer sizes; Just In Time (JIT)} | {No Buffer policy; Push; X Weeks site/external buffer; Just In Time (JIT)} | {X Weeks site/external storage buffer; Just In Time (JIT)}
Logistic system configuration | Who manages (operates) the logistics of materials on site? | {Subcontractors; GC site managers; Independent logistic team} | The subcontractors are in charge of inventory management | The subcontractors are in charge of inventory management under the company supervision
Materials delivery planning | Who plans material deliveries? | {Subcontractor; Logistics team; Site Team; GC head office procurement} | The subcontractor's responsibility | The site team (foremen, site manager, site engineer)
Materials delivery coordination | Who coordinates material delivery with drivers? | {Subcontractor; Site Team; A dedicated department} | {Subcontractor; Site Team; A dedicated department} | {Subcontractor; Site Team; A dedicated department}
Equipment Management
Infrastructure equipment | Who owns the infrastructure equipment? | {Rented ; Owned by the company} | {Rented ; Owned by the company} | {Rented ; Owned by the company}
Production equipment | Who owns the equipment? | {Rented ; Owned by the company} | {Rented ; Owned by the company} | {Rented ; Owned by the company}
Hand tools policy | Who provides hand tools for trades? This is a policy decision that determines whether hand tools will be a cause of wasted time | {GC; Subcontractor; Both} | {GC; Subcontractor} | {GC; Subcontractor}
Product changes
Coordinating | How are product changes coordinated through the production line? | {Daily meetings; BIM 360; WhatsApp; E-mails} | Daily meetings, WhatsApp, and E-mails | Daily meetings, WhatsApp, and E-mails
Documenting | How are product changes documented through the production line? | {Paper; BIM 360; WhatsApp; E-mails; Sitedrive} | Daily meetings, WhatsApp, and E-mails | Daily meetings, WhatsApp, and E-mails
Process changes
Coordinating | How are process changes coordinated through the production line? | {Daily meetings; BIM 360; WhatsApp; E-mails} | Daily meetings, WhatsApp, and E-mails | Daily meetings, WhatsApp, and E-mails
Documenting | How are process changes documented through the production line? | {Paper; BIM 360; WhatsApp; E-mails; Sitedrive} | WhatsApp or None | WhatsApp or None
Information and Communication Technologies
Operations flow information
Trades (Workers) production rate | What are the specific trade production rates? | {No information; Experience-based trade type production rate; Historical specific trade production rate; Trade production rate variation} | {No information; Experience-based trade type production rate; Historical specific trade production rate; Trade production rate variation} | {Experience-based trade type production rate; Historical specific trade production rate; Trade production rate variation}
Trade quality performance | What is the specific trade quality (rework/RFI) performance? | {No information; Experience-based trade type quality performance; Historical specific trade quality performance} | {No information; Experience-based trade type quality performance; Historical specific trade quality performance} | {Experience-based trade type quality performance; Historical specific trade quality performance}
Work control frequency | What is the frequency of collecting information on the amount of work completed? | {Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone} | {Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone} | {Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone}
Work control resolution | What is the level of resolution of the information collected on the amount of work completed? | {No control; The number of teams on the site a day/week; The number of workers in each team on site a day/week; Work amount preformed; Type of work preformed; Adding value work duration; Not adding value work duration} | {No control; The number of teams on the site a day/week; The number of workers in each team on site a day/week; Work amount preformed; Type of work preformed; Adding value work duration; Not adding value work duration} | { The number of teams on the site a day/week; The number of workers in each team on site a day/week; Work amount preformed; Type of work preformed; Adding value work duration; Not adding value work duration}
Trades constraints | Are prerequisite tasks mapped and how? | {Milestones; Gantt chart; Network diagram; Work Breakdown Structure; Computer network} | {Milestones; Gantt chart; Network diagram; Work Breakdown Structure; Computer network} | {Detailed Gantt chart; Network diagram; Work Breakdown Structure; Computer network}
Material consumption monitoring frequency | What is the frequency at which material consumption should be monitored or detected? | {No detection; Hourly; Daily; Weekly; Monthly} | {No detection; Hourly; Daily; Weekly; Monthly} | {Hourly; Daily; Weekly; Monthly}
Location occupation monitoring frequency | What is the frequency of collecting information on the location occupation and remaining? | {No monitoring; Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone} | {Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone} | {Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone}
Location occupation monitoring resolution | What is the level of resolution of the information collected on the location occupation? | {No information collected; Occupied/Free of work; Occupied/Free of materials; Location expected to be cleared} | {No information collected; Occupied/Free of work; Occupied/Free of materials; Location expected to be cleared} | {Occupied/Free of work; Occupied/Free of materials; Location expected to be cleared}
Control technologies | What type of technology is used for collecting the information? | {None; Site gate; Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings} | {None; Site gate; Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings} | {Site gate; Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings}
Process flow information (Product)
Product fabrication information LOD requirements | What LOD is required for information about the fabrication of the product(s), including materials? | {No materials list; Partial materials list; Detailed materials list; Detailed computerized list of materials} {Individual components; Sub-assemblies; Parameters; Type; Products; Generic categories} {Minimum (LOD100-200); Medium (LOD 300); Maximum LOD (400-500)} | {No materials list; Partial materials list; Detailed materials list; Detailed computerized list of materials} | {Partial materials list; Detailed materials list; Detailed computerized list of materials}
Product detailing process | What process is applied for developing the required level of detail for product fabrication information? | {None; Subcontractors provide shop drawings for review; Full VDC Process; partial VDC process for selected products} | {No materials list; Partial materials list; Detailed materials list; Detailed computerized list of materials} | {Partial materials list; Detailed materials list; Detailed computerized list of materials}
Product equipment information requirements | What information is required about the equipment needed to build the product? | {No equipment list; Partial equipment list; Detailed equipment list; Detailed computerized list of materials} | {No equipment list; Partial equipment list; Detailed equipment list; Detailed computerized list of materials} | {Partial equipment list; Detailed equipment list; Detailed computerized list of materials}
Performance monitoring technologies | What type of technology is used for collecting product information? | {Site gate; Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings}
Control technologies | What type of technology is used for collecting the information? | {Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings; Temperature and humidity measurement}
Logistics flow information
Materials location monitoring frequency | What is the frequency of collecting information on the materials location and remaining? | {No monitoring; Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone} | {Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone} | {Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone}
Materials inventory monitoring frequency | What is the frequency and extent of monitoring the material inventory? | {No monitoring; Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone} | {No monitoring; Real Time monitoring; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone} | {Real Time; Hourly; Daily; Two days; Weekly; Monthly; According to a subcontractor's report; At the completion of a milestone}
Control Technologies | What type of technology is used for collecting material status information? | {Self reporting; Computer vision; Laser scans; Photos; 360 video; Photogrammetry; RFID/BLE; Voice recordings}
Equipment location and status | What type of monitoring is implemented to maintain the equipment? | {There is no inspection; Manual reports; Regular inspections and preventive maintenance schedules; A computerized maintenance management system; Maintenance logs are kept to document the maintenance activities performed on the equipment; Real-time monitoring systems} | {There is no inspection; Manual reports; Regular inspections and preventive maintenance schedules; A computerized maintenance management system; Maintenance logs are kept to document the maintenance activities performed on the equipment; Real-time monitoring systems} | {Manual reports; Regular inspections and preventive maintenance schedules; A computerized maintenance management system; Maintenance logs are kept to document the maintenance activities performed on the equipment; Real-time monitoring systems}
Control Technologies | What type of technology is used for collecting equipment status information? | {Self reporting; RFID/BLE; Voice recordings}
Design status monitoring | What is the status of completing the design information? | {There is no tracking of the completion of the design; Completed before the project starts; Regular design reviews} | {There is no tracking of the completion of the design; Completed before the project starts; Regular design reviews} | {Completed before the project starts; Regular design reviews}
Platforms / Software
Production status dashboard system | What technological tools to are implemented to support information and communication? | {None; Data Visualization Tool e.g. Power BI; Project management e.g. Sitedrive} | None | None
Materials takeoff |  | {Manual; Word; Excel; BIM platforms; PDF-based collaboration and markup tools; Cloud-based construction takeoff; Estimating software}
Equipment status |  | {None; Manual; Digital Self reporting; RFID/BLE; 'Black Box' for heavy equipment}
Schedule planning |  | {Manual; Word; Excel; Cloud-based construction takeoff} | MS project | P6, MS project
Schedule control |  | {Word; Excel; collaborative whiteboarding e.g. Miro; Project management e.g. Sitedrive, Tocoman; Site whiteboard; Site monitor} | Manually updates | Manually updates
Design coordination |  | {Manual; PDF-based collaboration and markup tools; BIM e.g. Revit, Solibri, Tekla, Simplebim; Cloud-based construction management e.g. BIM 360; Dedicated software} | Manually | {BIM 360; Solibri; Tekla; Simplebim}
Quality control |  | {Visually; Dedicated software e.g. Concrete Quality Control} | {Manually; Excel; Word; Concrete Quality Control} | {Manually; Excel; Word; Concrete Quality Control}
Budget control |  | {Word; Excel; collaborative whiteboarding e.g. Miro; Project management e.g. Sitedrive, Tocoman, Vico, Microsoft Business Central} | {Excel; Vico; tocoman; Microsoft Business Central} | {Vico; tocoman; Microsoft Business Central}
Procurement |  | {Manual; Emails; Instant messaging e.g. WhatsApp; PDF-based collaboration and markup tools; BIM e.g. Revit, Tekla, Simplebim; Cloud-based construction management e.g. BIM 360; Dedicated software e.g. Solibri, Zeroni} | {Excel; BIM model; Email; Solibri; Zeroni; WhatsApp} | { BIM model; Email; Solibri; Zeroni; WhatsApp}
Safety |  | {Dedicated software e.g. Zeroni; Email; Instant messaging e.g. WhatsApp} | {Zeroni; Email; WhatsApp} | {Zeroni; Email; WhatsApp}
Logistics |  | {Dedicated software e.g. Zeroni; Email; Instant messaging e.g. WhatsApp} | {Zeroni; Email; WhatsApp} | {Zeroni; Email; WhatsApp}
Commercial Terms
Contract
Type | What is the contract type? | {DBB; DB; CM; CM@Risk; IPD; Other} | {DBB; DB; CM} | {DBB; DB; CM}
Introduction of construction expertise | At what stage of the project design and planning process does the GC become involved? | {Program; Initial/ Final/ Detailed design; Production planning} | {Program; Initial/ Final/ Detailed design; Production planning} | {Program; Initial/ Final/ Detailed design; Production planning}
GC payment method | What payment methods are used for the GC? | {Quantities; Percentage from the project cost}
Designers Payment | What payment methods are used for the designers? | {Hourly; Percentage from the project cost} | {Hourly; Percentage from the project cost} | {Hourly; Percentage from the project cost}
Designers LOD specification | What is the required project LOD? | {Minimum (LOD100-200); Medium (LOD 300); Maximum LOD (400-500)} | {Minimum (LOD100-200); Medium (LOD 300); Maximum LOD (400-500)} | {Medium (LOD 300); Maximum LOD (400-500)}
Control and Flexibility of The GC
Risk | What is the level of risk associated with the project? | {No risk; X% from the project cost; Critical project, maximum risk, the project will determine if the company finishes the year in profit or loss} | {No risk; X% from the project cost; Critical project, maximum risk, the project will determine if the company finishes the year in profit or loss} | {No risk; X% from the project cost; Critical project, maximum risk, the project will determine if the company finishes the year in profit or loss}
Flexibility for Design Changes during production | What is the degree of design flexibility afforded by the project? | {None; Property values; Dimensional changes; Topological changes} | {None; Property values; Dimensional changes; Topological changes} | {None; Property values; Dimensional changes; Topological changes}
Design Control | To what extent does the GC have control over the design of the project? | {No control; Limited control over architecture/ structural/ plumbing/ HVAC/ electricity; Design; Full Control} | {No control; Limited control over architecture/ structural/ plumbing/ HVAC/ electricity; Design; Full Control} | {Limited control over architecture/ structural/ plumbing/ HVAC/ electricity; Design; Full Control}
Operating Control | To what extent does the GC have control over the operating of the project? | {No control; Limited control; Full control} | {No control; Limited control; Full control} | {Limited control; Full control}
Cash Flow | What are the project cash flow limitations? | {No limitations; Materials purchases limitation; Labor limitation} | {Maximum; Minimum ;Average cash flow} | {Maximum; Average cash flow}
Trade employment
Employment conditions | What are the employment conditions? | {Direct employment; Employment through a human resources contractor; Employment of subcontractors} | Employment through a human resources contractor and employment of subcontractors | Employment through a human resources contractor and employment of subcontractors
Remuneration (wage) conditions | What are the wage conditions? | {Hourly; Daily; Monthly (global payment); By product} | By product (square m/ unit etc.) | By product (square m/ unit etc.)
Induction of new workers (on-boarding) | How are new employees inducted on the site? | {There is no conversation with the new employees on behalf of the company; There is an introductory conversation only for new employees; Presenting the work status and work methodology; ___ hours/days Professional qualification required by the company} | There is no conversation with the new employees on behalf of the company | Presenting the work status and work methodology for new employees
Organizational Structure
Hierarchy
Departments/Groups/Crews | What are the different departments, groups, or crews involved in the project? | {Client representation; Design; IT; Safety; Quality; Accounting; Procurement} | Developer, Clients (apartment purchases), Design, Accounting, HR, Procurement (contains safety and quality),suppliers. | Developer, Clients (apartment purchases), Design, IT, Accounting, HR, Procurement (contains safety and quality), logistics and suppliers.
Subordination (departments) | What is the subordination structure of the departments involved in the project? | {Matrix; Direct control} | {Matrix; Direct control} | {Matrix; Direct control}
Functional roles | What are the functional roles involved in the project? | {Manager; Designer; Finance; Quality} | Developer, Clients (apartment purchases), Designers, Accounting, Procurement, business unit managers, site managers, foremen, subcontractors, workers, and suppliers. | Developer, Clients (apartment purchases), Designers, Accounting, Procurement, business unit managers, site managers, foremen, subcontractors, workers, and suppliers.
Subordination (roles) | What is the subordination of the departments involved in the project? | {}
Functional role parameters
Scope/responsibility | What is the scope or responsibility of the functional roles involved in the project? | {Ordering materials; IT support; Generate reports} | Procurement: Contracting with suppliers, suppliers performance, materials compliance, monitoring the quality of suppliers, managing monitoring and quality and safety control, procurement of materials and equipment, contracting with subcontractors, inventory planning and vendor selection; Site team: schedule design and control, managing the site, maintaining safety regulations, supervising and maintaining quality, managing the project budget, ordering materials, ordering equipment, coordinating schedules, monitoring and control work performance. | Procurement: Contracting with suppliers, suppliers performance, materials compliance, monitoring the quality of suppliers, managing monitoring and quality and safety control, procurement of materials and equipment, contracting with subcontractors, inventory planning and vendor selection; Site team: schedule design and control, managing the site, maintaining safety regulations, supervising and maintaining quality, managing the project budget, ordering materials, ordering equipment, coordinating schedules, monitoring and control work performance.
Deliverables | What are the required deliverables for each functional role involved in the production phase? | {Generate reports; Design agreements} | {Generate reports; Design agreements} | Buildings, reports, recommendations, initiating optimization and improvement processes, contracts.